# Instructions for Using the
NEPA Projects Tracking Spreadsheet

## Introduction

The purpose of the NEPA Projects Tracking Spreadsheet is to systematically track the NEPA processing timeframes for all State Highway System projects under NEPA delegation.  The spreadsheet will be used to evaluate whether the streamlining objectives under NEPA delegation are being achieved.  The spreadsheet information will be incorporated into required monitoring reports related to NEPA delegation, including FHWA’s Section 6005 Pilot Program audit report; Caltrans’ quarterly performance  reports under Section 6004 and Section 6005; and Caltrans’ reports to the State Legislature related to its waiver of sovereign immunity, as required by Assembly Bill  (AB) 1039 and AB 2650.

The spreadsheet is to be completed by designated District/Region environmental staff   for all State Highway System projects (including locally-sponsored projects), including Categorical Exclusions (CE), environmental assessments (EA), environmental impact statements (EIS), and supplemental environmental documents (SED).  All applicable data fields on the spreadsheet must be completed based on the following guidance.  For some projects, especially projects processed with a CE, many of the data fields will not be relevant.  If a data field is not applicable, then indicate “NA”.

Districts may add data fields to the spreadsheet as necessary for other internal district purposes, such as tracking CEQA documents, however, the spreadsheet transmitted to headquarters must only include the original fields and options within those fields.   Districts may also create other versions of the tracking spreadsheet (a simplified version for CE projects, for example), as long as the NEPA Projects Tracking Spreadsheet is completed and kept up-to-date.

Each District/Region is responsible for keeping its spreadsheet up-to-date.  It is essential that the spreadsheet information be entered on an ongoing basis - data on milestones, actions, and decisions for each project should be entered as they occur - so that spreadsheet information requests can be responded to within five business days.  At a minimum, Headquarters will require that completed spreadsheets be submitted on a quarterly basis.  Each District/Region will also identify a contact person for its spreadsheet for responding to information requests and questions.

## How to Use the Spreadsheet

The NEPA Project Tracking Spreadsheet includes five worksheets:

- “Tracking NEPA Projects”:  This worksheet is the main spreadsheet for tracking NEPA processing timeframes, including those related to Section 106 of the National Historic Preservation Act and Section 7 of the federal Endangered Species Act.

- “Section 4(f)”:  This worksheet tracks Section 4(f) evaluations for CE projects and for those projects in which the Section 4(f) evaluation is not circulated with the draft environmental document (DED) and/or final environmental document (FED). Projects in which the Section 4(f) evaluation is a part of the environmental document should be tracked on the main spreadsheet.

- “De-minimis 4(f)”: This worksheet tracks SAFETEA-LU Section 6009 reporting requirements for de-minimis 4(f) findings.

- “1039 Agencies”:  This worksheet contains a comprehensive list of state and federal agencies that typically comment on DEDs, along with the relevant acronyms to be used in the spreadsheet.

- “Comments Codes”:  This worksheet identifies a variety of possible comment codes that can used to explain the reasons for delayed processing and approval timeframes. One or more comment codes can be entered, as appropriate.  If further explanation is required to describe reasons for delays, then use the “Other General Project Comments” column.

The main “Tracking NEPA Projects” spreadsheet is divided into fourteen major sections for identifying each project and tracking major environmental approvals. The twelve major sections are described briefly below:

- “Project Identification and General Information” identifies each project.  When printing the spreadsheet, the District and Expenditure Authorization (EA) columns will automatically print on each page.

- “Project Start Up” identifies dates associated with the start of the NEPA process.

- “NEPA/404 Applicable?” identifies whether the NEPA/404 integration process has been invoked.  The “it (interagency tracking)” database is to be used for tracking timeframes related to the integration process.

- “Section 4(f) Applicability” identifies whether Section 4(f) applies and the type of Section 4(f) finding.

- “Draft ED” identifies major milestones related to the DED, including Caltrans District quality control (QC), Legal, and Headquarters (HQ) reviews, and approval of the DED for public review.

- “State and Federal Commenting Agencies per 1039 Report” identifies those State and Federal agencies that commented on the DED during the public review process.  This information is tracked in the spreadsheet because the State Legislature has required that Caltrans include this information in the AB 1039/2650 reports.

- “Section 106” identifies major milestones related to the approval of the Finding of Effect (FOE) report and the Memorandum of Agreement (MOA) under Section 106 of the National Historic Preservation Act.  The “it” database is to be used for other Section 106 milestones for the 106 Programmatic Agreement Annual Report.

- “Section 7/EFH” identifies dates for findings made by U.S. Fish and Wildlife Service (FWS) and National Marine Fisheries Service (NMFS) under Section 7 of the federal Endangered Species Act (ESA) and by NMFS for Essential Fish Habitat (EFH) evaluations under the Magnuson-Stevens Fishery Conservation and Management Act (MSA).

- “Air Quality Conformity” identifies dates for when the air quality conformity determination request was submitted to FHWA and the date FHWA provided a conformity determination.

- “Final ED” identifies major milestones related to the FED, including Caltrans District QC, Legal, and HQ reviews, and approval of the FED.

- “Record of Decision (ROD)” identifies dates in which the ROD was reviewed and approved.

- “Re-validation” identifies when re-validations were completed for a project environmental document or CE that needed to be updated or needs a new document/CE.

- “Environmental Commitments” identifies major milestones related to tracking and implementing environmental commitments called for in the ED.

- “Other General Project Comments” provides space to enter general open-ended comments regarding the NEPA processing timeframes. This field has no character limit and may be expanded as necessary.  To change the row height to fit the contents, double-click the boundary below the row heading on the left side of the page.

The sections identified above related to the DED, Section 106, Section 7/EFH, FED, and ROD contain “Comments” columns in which comment codes may be entered to explain the reasons for delayed processing and approval timeframes.  As noted above, additional open-ended comments may also be provided in the “Other General Projects Comments” column.

## Explanation of Spreadsheet Columns and Interactive Elements

Table 1 provides an explanation of each of the columns on the Tracking NEPA Projects spreadsheet.  Table 2 defines the columns in the Section 4(f) spreadsheet. Table 3 defines

acronyms used in the spreadsheet.

The “Tracking NEPA Projects” and “Section 4(f)” spreadsheets use pop-up comments and drop-down menus that provide additional assistance when entering information:

- Pop-ups: Pop-up comments are used in those cells that provide reminders or instructions.  These cells have a red triangle in the top right corner.  A pop-up comment will appear when the mouse is rolled over these cells.  All “Comments” cells except for “Other General Project Comments” have pop-up comments that reference the “Comments Codes” worksheet.  The “Section 4(f) Applicability” and “State & Federal Commenting Agencies Per 1039 Report” cells also have pop-up comments that reference the applicable worksheets.

- Drop-down menus: Drop-down menus are used in those cells that identify a range of possible pre-defined entries.  A dropdown arrow appears to the right of the cell when the cell is clicked.  Cells with drop-down menus cannot be modified, and will not accept entries that do not match the drop-down list.  Only one entry can be selected from each drop-down menu.

| Table 1. Explanation of “Tracking NEPA Projects” Spreadsheet Columns |
| --- |
| Column Name | Information to be Provided in Column |
| Project Identification |
| Dist.-EA | Two-digit District number and five-digit Expenditure Authorization number (two numbers should be separated by a hyphen). Include a zero before Districts 1 through 9 (01, 02, etc). Do not include the sixth digit of EA number indicating phase of project |
| Co | County |
| Rte | State highway route number |
| Post mile | Start and end post mile |
| General Information |
| Project Name/Description | Project name or description |
| Agency | Identify Caltrans for Caltrans-sponsored projects on the State Highway System. Identify name of local agency if locally sponsored project on the State Highway System. |
| NEPA Doc type | Click on the appropriate document type in the drop down box. |
| CT NEPA Assignment | Click yes if Caltrans has been assigned NEPA under Sections 6004 or 6005. Click no if FHWA has retained NEPA responsibilities. |
| Delivery Plan Information |
| DED Current | Enter planned DED delivery date from the Delivery Plan only when DED Delivery Plan date is in current FY. Do not enter future year dates. |
| PAED Current | Enter current FY delivery date only from the Delivery Plan (if PAED date is not in current FY, do not enter). |
| Project Contact Information |
| Name | Enter the name of the project contact, usually the environmental senior or generalist/environmental coordinator. |
| Phone | Enter the phone number of the project contact. |
| Project Start-Up |
| NOI | For EIS projects, date Notice of Intent (NOI) published in the Federal Register |
| Begin Env. Studies | Date that environmental studies begin based on District/Region practice (such as date of Begin Environmental Studies memo, when charges to WBS code 165 begin, etc). If EIS project, use date of NOI. |
| Class of Action Determination | Enter the date the Class of Action Determination concurrence was obtained from the Headquarters Environmental Coordinator for EA and EIS projects. |
| NEPA/404 Applicable? | Click “yes” if the NEPA/404 integration process is invoked. Otherwise, click “no”. Use “it “database for tracking integration process timeline. |
| Section 4(f) Applicability |  |
| Y/N | Click “yes” if Section 4(f) applies; click “no” if Section 4(f) does not apply. |
| Type | If Section 4(f) applies, click on applicable Section 4(f) finding and/or type in the drop-down box, and complete the Section 4(f) worksheet if appropriate. If Section 4(f) does not apply, you may leave this field blank. The Section 4(f) worksheet is to be used for CE projects and for those in which the Section 4(f) evaluation is not circulated with the DED and/or FED. If a project has 4(f) resources with de-minimis findings, document the de-minimis findings in the “De-minimis 4(f )” worksheet. If a project has multiple 4(f) evaluations (such as a programmatic and individual evaluation), document the timeline for the highest level 4(f) evaluation and use the ‘Other General Project Comments” column to document the multiple 4(f) evaluations. |
| Draft ED |
| Admin DED Complete; Begin Dist. QC | Date that the administrative DED is complete, and the District QC process begins. For CE projects, enter NA in DED columns. |
| Dist. DED QC Complete | Date that Caltrans District QC review is completed. |
| Submit Admin DED to Legal | Date that District submits DED to Caltrans Legal for review. Legal review is required for all EISs. If Legal reviews an EA, include this date. |
| Legal Comments on Admin DED | Date that Caltrans Legal completes its review of DED. If multiple review cycles, enter date that Legal provides final comments and note multiple reviews in comments section. |
| Dist. Response to Legal Comments | Date that District completes final revisions to DED based on Legal comments. |
| Admin DED Legal Review Complete | Date of Caltrans Legal sign-off of DED. |
| Submit Admin DED to HQ | Date that District submits DED to Caltrans HQ for review. HQ’s review is required for all EISs and complex EAs. If HQ reviews a routine EA, include this date. |
| HQ Comments on Admin DED | Date that HQ completes its review of DED. If multiple review cycles, enter date that HQ provides final comments and note multiple reviews in comments section. |
| Dist. Response to HQ Comments | Date that District completes final revisions to DED based on HQ’s comments. |
| Comments on DED Review | Enter applicable comment codes from Comment Codes worksheet. If further explanation is required to describe reasons for delays (including delays unrelated to environmental such as those associated with the Draft Project Report), then use the “Other General Project Comments” column. |
| DED Ready for Signature | Date that DED title page is deemed to be ready for signature. For EISs and complex EAs, HQ’s input is required to make this determination. |
| DED Signed | Date that DED title page is signed. |
| DED Circulated | Date that draft EIS or draft EA public review period begins based on published notices. |
| Public Hearing/Meeting | Date that public hearing/meeting held on DED. if applicable. If multiple public hearings or meetings were held, only enter date of last public meeting/hearing. If no public meeting/hearing held, enter NA. |
| DED Public Comment Period Closed | Date that draft EIS or draft EA public review period ends based on published notice(s). |
| State & Federal Commenting Agencies Per 1039 Report | Enter acronyms (from “1039 Agencies worksheet”) of each agency that commented on the DED during the public review period. If an agency is not listed on the worksheet, then enter the agency’s name using its standard acronym. |
| Section 106 |
| Section 106 FOE | Click on the applicable Finding of Effect (FOE) in the drop-down box: None, No Historic Property Affected (NHPA), No Adverse Effect with Standard Conditions (NAE/SC), No Adverse Effect (NAE), and Adverse Effect (AE). |
| Submit FOE to HQ | Date that District submits NAE/AE to HQ for review. |
| HQ Submit FOE to SHPO | Date that HQ submits NAE/AE to SHPO for concurrence. |
| SHPO concurs | Date that SHPO approves the NAE/AE. |
| Submit MOA to HQ | Date that District submits 106 MOA to HQ for review. |
| HQ Submit MOA to SHPO | Date that HQ submits the 106 MOA to SHPO for consultation. |
| MOA signed | Date of the last signature on the MOA. |
| Comments on 106 Consultation | Enter applicable comment codes from Comment Codes worksheet. If further explanation is required to describe reasons for delays, then use the “Other General Project Comments” column. |
| Section 7/EFH Consultation |
| Submit BA/BE to FWS | Date that Caltrans submits Section 7 biological assessment (BA) or biological evaluation (BE) to the FWS for review. |
| FWS Finding | Click on the applicable finding: “Letter of concurrence” or “Biological Opinion (BO)”. |
| FWS Finding | Date of the letter of concurrence or of the BO. |
| Comments on FWS Consultation | Enter applicable comment codes from Comment Codes worksheet. If delays in environmental approvals occurred due to unique project circumstances related to biological resources such as impacts related to a Wild and Scenic River or the Marine Mammal Protection Act, explain the reasons for delay in the “Other General Project Comments” column. |
| Submit BA/BE/EFH to NMFS | Date that Caltrans submits Section 7 BA or BE (and EFH evaluation, if applicable) to NMFS. If no BA or BE is prepared, date that Caltrans submits EFH evaluation to NMFS. If both ESA and MSA apply and reports submitted on different dates, enter the latter of the two dates. |
| NMFS Finding | Click on the applicable finding: “Letter of concurrence”, “BO”, “EFH” if EFH only without Section 7, “Letter of concurrence and EFH”, or “BO and EFH”. |
| EFH Recommendation | Date that Caltrans receives recommendations from NMFS on EFH evaluation |
| Caltrans Response to EFH | Date that Caltrans responds to NMFS’ recommendations on EFH evaluation |
| NMFS Section 7 Finding | Date of letter of concurrence or of the BO. |
| NMFS EFH Finding | Date of letter of concurrence on EFH consultation. |
| Comments on NMFS Consultation | Enter applicable comment codes from Comment Codes worksheet. If delays in approvals occurred due to unique project circumstances such as bioacoustic or fish passage impacts, explain in the “Other General Project Comments” column. |
| Air Quality Conformity |
| Request to FHWA | Date that Caltrans submits conformity request to FHWA. |
| FHWA Determin. | Date that FHWA signs the air quality conformity determination. |
| Final ED |
| Admin FED Complete; Begin Dist. QC | Date that the administrative FED is complete, and the District QC process begins. For CEs, skip to “CE/FED Ready for Signature” column. |
| Dist. FED QC Complete | Date that Caltrans District QC review is complete. |
| Submit Admin FED to Legal | Date that District submits FED to Caltrans Legal for review. Legal sufficiency review is required for all final EISs. If Legal reviews a revised EA/FONSI, include this date. |
| Legal Comments on Admin FED | Date that Caltrans Legal completes its review of FED. If multiple review cycles, enter date that Legal provides final comments and note multiple review in the comments section. |
| Dist. Response to Legal Comments | Date that District completes final revisions to FED based on Legal comments. |
| Admin FED Legal Sufficiency Complete | Date of Caltrans Legal sufficiency determination for FED. |
| Submit Admin FED to HQ | Date that District submits FED to Caltrans HQ for review. HQ review is required for all final EISs and complex EAs. If HQ reviews a revised routine EA, include this date. |
| HQ Comments on Admin FED | Date that HQ completes its review of FED. If multiple review cycles, enter date that HQ provides final comments and note multiple review in the comments section. |
| Dist. Response to HQ Comments | Date that District completes final revisions to FED based on HQ’s comments. |
| Comments on FED Review | Enter applicable comment codes from Comment Codes worksheet. If further explanation is required to describe reasons for delays (including delays unrelated to environmental such as those associated with the Project Report), then use the “Other General Project Comments” column. |
| CE/FED Ready for Signature | Date that CE or FED title page is deemed to be ready for signature. For EISs and complex EAs, HQ’s input is required to make this determination. |
| CE/FONSI/FEIS Signed | Date that FONSI or FEIS title page is signed. If signing of the FED is delayed for any reason, such as the availability of project funding, describe the reason for the delay in the “Other General Project Comments” column. |
| ROD |
| ROD to HQ | Date that District submits the ROD to HQ for review. |
| HQ Review Complete | Date that HQ completes its final review of ROD. |
| Comments on ROD Reviews | Enter applicable comment codes from Comment Codes worksheet. If further explanation is required to describe reasons for delays, then use the “Other General Project Comments” column. |
| ROD Signed | Date that the District Director signs the ROD. |
| ROD Noticed in Federal Register | Date that FHWA publishes the ROD in the Federal Register. |
| Re-Validation |
| Enter data only if the original ED or CE is… | Enter re-validations for projects where the environmental document needed to be updated or is no longer valid. For projects where a new ED is required, enter project information associated with the new ED on a separate line |
| Re-Validation Signed | Date that re-validation is signed |
| Environmental Commitments |
| ECR required? Y/N | Click “Yes” if a ECR is required, click “No” if a ECR is not required; only when no environmental commitments are involved in the project. |
| ECR Prepared | Date that the Environmental Commitments Record (ECR) is completed prior to completion of Project Approval/Environmental Document (PA/ED). |
| Environmental Cert. Signed | Date that the Environmental Branch/Office Chief signs the Environmental Certification form at RTL. |
| Certificate of Environmental Compliance Signed | Date that the Resident Engineer and the Environmental Branch/Office Chief (or designee) sign the Certificate of Environmental Compliance. |

| Table 2. Explanation of “Section 4(f)” Spreadsheet Columns |
| --- |
| Column Name | Information to be Provided in Column |
| Project Identification |
| Dist.-EA | Two-digit District number and five-digit Expenditure Authorization number (two numbers should be separated by a hyphen). Include a zero before Districts 1 through 9 (01, 02, etc). Do not include the sixth digit of EA number indicating phase of project |
| 4(f) Applicability | Click on applicable Section 4(f) finding and/or report: De-minimus only, De-minimis plus Programmatic, De-minimis plus Individual, Programmatic Plus Individual, Programmatic Only, or Individual Only. If a project has multiple 4(f) resources with de-minimis findings, document the multiple de-minimis findings in the “Other General Project Comments” column and the “De minimis 4(f) worksheet. If a project has multiple 4(f) evaluations (such as a programmatic and individual evaluation), document the timeline for the highest level 4(f) evaluation and use the ‘Other General Project Comments” column to document the multiple 4(f) evaluations. |
| Draft 4(f) |
| Admin Draft 4(f) Complete; Begin Dist QC | Date that the administrative draft Section 4(f) evaluation is complete, and the District QC process begins. |
| Dist Draft 4(f) QC Complete | Date that Caltrans District QC review is complete. |
| Submit Draft 4(f) to Legal | Date that District submits draft Section 4(f) evaluation to Caltrans Legal for review. Legal review is required for all individual Section 4(f) evaluations. If Legal reviews a programmatic Section 4(f) evaluation, include this date. |
| Legal Comments on Draft 4(f) | Date that Caltrans Legal completes its final review of the draft Section 4(f) evaluation. |
| Dist. Response to Legal Comments | Date that District completes final revisions to draft Section 4(f) evaluation based on Legal comments. |
| Draft 4(f) Legal Review Complete | Date of Caltrans Legal sign-off of draft Section 4(f) evaluation. |
| Submit Draft 4(f) to HQ | Date that Legal/District submits draft Section 4(f) evaluation to Caltrans HQ for review. HQ’s review is required for all individual Section 4(f) evaluations. If HQ reviews a programmatic Section 4(f) evaluation, include this date. |
| HQ Comments on Draft 4(f) | Date that HQ completes its final review of draft Section 4(f) evaluation. |
| Dist. Response to HQ Comments | Date that District completes final revisions to draft Section 4(f) evaluation based on HQ’s comments. |
| Draft 4(f) Ready for Signature | Date that draft Section 4(f) evaluation is deemed ready for signature. For individual Section 4(f) evaluations, HQ’s input is required to make this determination. |
| Comments on Draft 4(f) Review | Enter applicable comment codes from Comment Codes worksheet. If further explanation is required to describe reasons for delays, then use the “Other General Project Comments” column. |
| Admin Final 4(f) Complete; Begin Dist QC | Date that the administrative final Section 4(f) evaluation is complete, and the District QC process begins. |
| Dist Final 4(f) QC Complete | Date that Caltrans District QC review is complete. |
| Submit Final 4(f) to Legal | Date that District submits final Section 4(f) evaluation to Caltrans Legal for review. Legal review is required for all individual Section 4(f) evaluations. If Legal reviews a programmatic Section 4(f) evaluation, include this date. |
| Legal Comments on Final 4(f) | Date that Caltrans Legal completes its final review of the final Section 4(f) evaluation. |
| Dist. Response to Legal Comments | Date that District completes final revisions to final Section 4(f) evaluation based on Legal comments. |
| Draft 4(f) Legal Sufficiency Complete | Date of the Caltrans Legal legal sufficiency determination for final Section 4(f) evaluation. |
| Submit Final 4(f) to HQ | Date that Legal/District submits final Section 4(f) evaluation to Caltrans HQ for review. HQ’s review is required for all individual Section 4(f) evaluations. If HQ reviews a programmatic Section 4(f) evaluation, include this date. |
| HQ Comments on Final 4(f) | Date that HQ completes its final review of final Section 4(f) evaluation. |
| Dist. Response to HQ Comments | Date that District completes final revisions to final Section 4(f) evaluation based on HQ’s comments. |
| Final 4(f) Ready for Signature | Date that final Section 4(f) evaluation is deemed ready for signature. For individual Section 4(f) evaluations, HQ’s input is required to make this determination. |
| Comments on Final 4(f) Review | Enter applicable comment codes from Comment Codes worksheet. If further explanation is required to describe reasons for delays, then use the “Other General Project Comments” column. |

| Table 3. Explanation of “De-minimis 4(f)” Spreadsheet Columns |
| --- |
| Column Name | Information to be Provided in Column |
| Senior | Enter name of project Senior |
| Coordinator | Enter name of project Generalist/Coordinator |
| EA | Enter Expenditure Authorization |
| Project Location County/City | Enter county and city where project is located as applicable |
| Route | Enter route number |
| Project Name | Enter project name |
| Length (miles) | Enter project length in miles |
| Description (B, I, N, S, TE, W, O) | Enter the corresponding letter that best describes the project: B = bridge, I = intersection/interchange, N = new alignment, S = safety, TE = enhancement, O = other |
| Project Cost | Enter Capitol Cost of project including Construction/Right of Way capitol costs |
| Class of Action | Enter environmental document or determination type |
| # 4(f) Resources | Enter the number of 4(f) resources |
| 4(f) Resources | Describe 4(f) resource(s) |
| # 4(f) de minimis impact findings | Enter the number of de minimis findings |
| De Minimis Impacts | Describe de minimis impacts for each resource |
| De Minimis Mitigation | Describe de minimis mitigation for each resource |
| Size of de minimis use (acres) | Enter the acreage of the de minimis impact for each resource |
| Type of de minimis resource (H, P, R, or W | Enter the corresponding letter that best describes the de minimis resource(s). H = Historic, P = Park, R = Recreation, W = wildlife refuge |
| Date of 4(f) de minimis finding | Enter the date the de minimis finding was made by Caltrans. Note: This could be earlier or the same date as the FED/CE. |
| Project Status | Enter most recently completed project milestone and current project phase. |
| Construction Start | Enter planed construction start date. |
| Construction End | Enter the planed construction end date. |

| Table 4. Acronym List |
| --- |
| Acronym | Definition |
| AE | Adverse Effect |
| BA | Biological Assessment |
| BE | Biological Evaluation |
| BO | Biological Opinion |
| CE | Categorical Exclusion |
| Co. | County |
| DDR | District Delayed Response |
| DED | Draft Environmental Document |
| Dist. | District |
| EA | Environmental Assessment – or- Expenditure Authorization |
| ECR | Environmental Commitments Record |
| EFH | Essential Fish Habitat |
| EIS | Environmental Impact Statement |
| ESA | Federal Endangered Species Act |
| FED | Final Environmental Document |
| FEIS | Final Environmental Impact Statement |
| FHWA | Federal Highway Administration |
| FOE | Finding of Effect |
| FONSI | Finding of No Significant Impact |
| FWS | U.S. Fish and Wildlife Service |
| HQ | Caltrans Headquarters |
| HQDR | Headquarters Delayed Response |
| LDR | Legal Delayed Response |
| MOA | Memorandum of Agreement |
| MRD | Multiple Reviews by District |
| MRHQ | Multiple Reviews by Headquarters |
| MRL | Multiple Reviews by Legal |
| MRPA | Multiple Reviews by Participating Agencies |
| MRRA | Multiple Reviews by Regulatory Agency |
| MSA | Magnuson-Stevens Fishery Conservation and Management Act |
| NA | Not Applicable |
| NAE | No Adverse Effect |
| NAE/SC | No Adverse Effect with Standard Conditions |
| NEPA | National Environmental Policy Act |
| NHPA | No Historic Property Affected |
| NMFS | National Marine Fisheries Service |
| NOI | Notice of Intent |
| PA/ED | Project Approval/ Environmental Document |
| QC | Quality Control |
| RADR | Regulatory Agency Delayed Response |
| RD | Revisions Delayed |
| ROD | Record of Decision |
| Rte. | Route |
| RTL | Ready to List |
| SED | Supplemental Environmental Document |
| SHPO | State Historic Preservation Officer |